## Risk Regisiter Priority
Version | Q2 2025/26
Date | 2025-11-07
New Risk added | AE 8/9/24/25/26/27/28/29
Treated risked removed | AE 3/4/5/10/14/15/16/17/18/11/19/21/8/9/25/13/20/26
Risk ID
Funding | Description | Inherent Risk | Control/ Mitigating Action | Residual Risk | Action Plan | Timescale | Target Risk | Owner | Board Sponsor
AE1 | Sport England discontinues support for Active Partnerships | 2 x 5 = 10 | Continue to articulate impact of AP and hold strong reputation. Current lottery award in place with core funding until 2027. | 3 x 3 = 9 | Sport England Active Partnerships review with begin in 2025 and will influence April 2027 funding. AE Exec team to feed into SE work and report back | 2026-09-01 | 2 x 2 = 4 | JF/ RH | WB
Governance | Description | Inherent Risk | Control/ Mitigating Action | Residual Risk | Action Plan | Timescale | Target Risk | Owner | Board Sponsor
AE7 | The host agency discontinue support to the partnership. Local Government structure/ reviews continue to have potential impact | 4 x 4 = 16 | Plan to shift to another host/ article benefits/ delivery and impact articulated | 4 x 4 = 16 | Scoping of potentail hosting options for AE once more in know on Devolution and AE29 | ongoing | 3 x 3 = 9 | JF/RH | BM
Strategy | Description | Inherent Risk | Control/ Mitigating Action | Residual Risk | Action Plan | Timescale | Target Risk | Owner | Board Sponsor
AE26 | Active Essex Foundation - support for its d evelopment and growth. | 3 x 3 = 9 | How do we work more closely together? Investigate opportunities around further grants, CSR and commercial opportunities that would benefit AEF | 3 x 3 = 9 | Scope grants/ CSR/ commercial opportunities and progress those most suitable. Scope out closer working relationship/ maximise skills of both Boards. | on going | 2 x 2 = 4 | RH | BM
AE29 | Impact of Devolution. Current political uncertainty (local and nation) and its effect on the future of Active Essex | 4 x 4 = 16 | Local elections due for May 2025 postponed. LG restructure and Mayoral elections due May 26. LG restruture by April 2027 | 4 x 4 = 16 | Ensure Board/ SLT are aware of direction of travel for Devolution. Ensure AE Exec/ Board engages at political level and Senior officer. Regular updates to Board | 2026-04-01 | 3 x 3 = 9 | JF | WB
Delivery | Description | Inherent Risk | Control/ Mitigating Action | Residual Risk | Action Plan | Timescale | Target Risk | Owner | Board Sponsor

## Risk Regisiter BAU
Version | Q3 2024/25
Date | 2026-01-08
New Risk added | AE 8/9/24/25/26/27/28/29
Treated risked removed | AE 3/4/5/10/14/15/16/17/18/11
Risk ID
Funding | Description | Inherent Risk | Control/ Mitigating Action | Residual Risk | Action Plan | Timescale | Target Risk | Owner | Board Sponsor
AE2 | Active Essex fails to meet Sport England grant return requirements | 2 x 5 = 10 | Ensure process/ reporting requirements are in place and grant conditions are fully met. | 1 x 3 = 3 | Robust financial procedures in place to monitor and report grant requirements every 6 months (October and April) | 2025-10-01 | 1 x 3 = 3 | RH | CR
Governance | Description | Inherent Risk | Control/ Mitigating Action | Residual Risk | Action Plan | Timescale | Target Risk | Owner | Board Sponsor
AE6 | Code of Good Governance criteria audit approved and AE compliance. Review every year 12 months to meet standards required | 3 x 3 = 9 | Action plan criteria need to met in order to maintain AP funding. | 3 x 3 = 9 | Current citeria all met and SE have signed off. Monitor for future updates and potential changes. | ongoing | 3 x 3 = 9 | RH | BM
AE 27 | AE Board doesn’t maintain its skills mix, expertise, diversity, values, model behaviours and commitment of Board members. Goverance code citeria is not met, Board members underperform, have conflicits of interest and Board members retire and corporate memory is lost and recruitment fails to provide suitable replacements. | 4 x 4 = 16 | Board recruited according to the skills required and following procedures agreed by the Governance paper. Ongoing training for Equality, Diversity & Inclusion including Inclusive Leaders programme. AE DIAP centrally to driving agenda. | 3 x 3 = 9 | Chair annual review and external 4 year review of Board & members skill set and ensure it is fit for purpose. Recruitment and on-boarding processes for the inclusion of Values expectations. Feeds into People, Culture Skills work. | 2026-07-01 | 2 x 2 = 4 | JF/RH | WB
Strategy | Description | Inherent Risk | Control/ Mitigating Action | Residual Risk | Action Plan | Timescale | Target Risk | Owner | Board Sponsor
AE12 | Reputation Risk. Board members adhere to code of conduct and the values of Active Essex as they join and exit the Board. | 3 x 3 = 9 | ToR and Nolan principals contained with governing documents outlining expectations of Board members. | 3 x 3 = 9 | Board members follow the principles contained within policy to ensure AE reputation is protected. Comms team to support with briefings and/ or queries. | ongoing | 3 x 3 = 9 | JF/RH | WB
AE25 | Support the future of Essex leisure working with Leisure Providers / Local authorities / contract holders | 4 x 4 = 16 | Use networks to scope, advocate and drive support into these groups | 3 x 3 = 9 | Group in place. LGR conversations focus on impact and potential operating models. | 2026-04-01 | 3 x 3 = 9 | JF | BM
AE 28 | Support / Advocate for the Sport and Physical Activity sector. Supporting clubs, organisations & local community groups who are working to increase physical activity levels with communities. | 4 x 4 = 16 | Facilitate, advocate and drive support into these groups | 3 x 3 = 9 | Create and drive networks, facilitated by AE to advocate, share practice and learn. Support the work of NGB's in this space with community sport sector | ongoing | 3 x 3 = 9 | HW | EL
Delivery | Description | Inherent Risk | Control/ Mitigating Action | Residual Risk | Action Plan | Timescale | Target Risk | Owner | Board Sponsor
AE 22 | Safeguarding - Internal: Ensure the AE has robust internal process/ training in place for staff and Board . Organisations Groups we fund have policy and procedure in place. | 3 x 4 = 12 | Work with AE leads to support the processes already in place and ensure they are fit for purpose. | 3 x 3 = 9 | Ensure staff are supported to implement policies and supported by line management structure of AE. | ongoing | 2 x 3 = 6 | HW | DS
AE 23 | Safeguarding: Externally - to champion policy and procedures to sector and provide independent check and challenge. Incorporate the need to champion and advocate Duty of care of participations, coaches and athletes | 3 x 4 = 12 | Work with AE leads to support the development of policy and guide best practice in this space. | 3 x 3 = 9 | Provide an independent voice to check and challenge and support AE lead in advocacy with external partners | ongoing | 3 x 3 = 9 | HW | DS
AE 24 | Lack of diversity of beneficiaries across Active Essex funded programmes or a perception of inequitable awards of funding. | 3 x 4 = 12 | Open and transparent processes to awarding funding against criteria. Delivery of targeted funding for under-represented groups (Together Fund, HAF, Local Delivery Pilot) | 3 x 3 = 9 | Ensure all funds have clear criteria and a transparent approval process. Add inclusion question to all application forms. Prioritise inclusive projects and projects for under-represented groups for upcoming funding streams | ongoing | 2 x 3 = 6 | HC | DS

## Treatment Guide
The Impact Guide is designed to assist risk owners and managers determine the scores applied to any risk. In the case of the host agency, a 5 x 5 scale for impact and likelihood is used.
Impact ranges from Insignificant (1) to Very Serious (5). Likelihood ranges from Very Low (1) to Very High (5). The combined scores on a 5 x 5 matrix will give scores ranging from 1 to 25. The scoring will be determined on the basis of the risk owner's opinion of the residual risk after taking account of their perception of the effectiveness of the existing controls.
The scoring matrix is as follows.
Likelihood of risk
1 – Very low
2 – Low
3 – Medium
4 – High
5 – Very high
If likelihood was assessed as very low (e.g. earthquake) it could be given a score of “less than 1” such that even
highest impact risks could attract on overall score of “less than 5”.
Impact of risk
1 – Insignificant
2 – Minor
3 – Moderate
4 – Serious
5 – Very serious
Total risk score (likelihood x impact)
1 – 6 Low
8 – 12 Medium
14 – 20 High
Over 20 Very high

## Treated Risk
AE3 | Essex County Council budget decreases and Covid impact reduces funding to Active Essex | 4 x 4 = 16 | Develop capacity/ plan for Active Essex to continue independently of ECC. | 4 x 3 = 12 | Need to develop other sources of income. Business Plan/ operation of Active Essex Foundation to be in place | 2021-10-01 | 2 x 3 = 6 | JF | CR | Remove
AE4 | Schools Forum funding discontinued | 5 x 4 = 20 | Scope potential for alternative income streams | 3 x 3 = 9 | Create alternative sources of funding to support operations. | 2022-01-01 | 3 x 3 = 9 | LM | EL | Remove
AE5 | Change to CYP organisation and funding | 3 x 3 = 9 | CYP deep dive / Revisit organisational outputs and operation in line with amended funding conditions | 3 x 3 = 9 | Respond with adapted organisational and programme plan. | 2021-12-01 | 2 x 2 = 4 | LM | EL | Remove
AE10 | Active Essex fails to produce a new strategy which is both inline with direction of sector and rejected by funders and stakeholders | 3 x 3 = 9 | Action plan developed with Senior team management and Board | 2 x 2 = 4 | Execution of action plan in period April / May 2021 | 2021-07-15 | 2 x 2 = 4 | JF/RH | WB | Remove
AE14 | Covid - 19 outbreak impacts on Local Authority Leisure facilities and contracts. Centres are unable to re-open with a profitable operationg model post outbreak as "new normal" takes effect | 3 x 5 = 15 | Develop capacity of the sector to adapt in the "new normal". | 3 x 4 = 12 | Respond to changes quickly and effectively. Funding sourced from Sport England to work with KKP | 2022-12-15 | 3 x 3 = 9 | JF | EL | Remove
AE15 | The Sport and Physical Activity Sector declines due to Covid-19 impact and the changes to everyday life this requires post lockdown. Organisations/ clubs/ groups and teams go out of business and particapation opportunites decrease as a result | 3 x 5 = 15 | Work with sector on new normal and a viable alternative structures required improve outcomes around physical activity. | 3 x 4 = 12 | Broker, signpost and play support role to ensure sector is best state possible to sustain and grow | 2022-12-15 | 3 x 3 = 9 | JF/RH | EL | Remove
AE16 | The health sector sees an unprecidented rise in the number of deconditioned adults and vunerable members of the community following the Covid pandemic. | 5 X 4 = 20 | Action plan developed with Board supporter and AE team leads |  | Execution of action plan including emerging project work around Find your Active. | 2022-12-15 |  | KH | DD | Remove
AE17 | 12 Local Authorities and 2 Unitaries suffer serious hardship and budgets are put under increased pressure. Resources are impacted as inequalities grow within Essex communities. | 3 x 5 = 15 | Develop capacity of the Local Authorities to adapt in the "new normal". | 3 x 4 = 12 | Adopt ABCD prinipals and Universal proportionalism. Expand reach of LDP into our areas | 2022-09-15 | 3 x 3 = 9 | JF/RH | DS | Remove
AE18 | Education sector is unable to recover to business as usually. With completing priorites physical activity levels amongst young peope fail dramatically | 3 x 5 = 15 | Work with education around policy and programmes to facilitate and enable activity to take place | 3 x 3 = 9 | Help translate guidenace and policy throught CYP work and team. Target programmes such as School Premium funding, Daily Mile and Satelitte clubs into areas of most need, based on data and insight. | 2022-09-15 | 3 x 3 = 9 | LM | EL | Remove
AE11 | New Sport England Strategy results in Inappropriate skills mix, expertise and commitment of Board members. Board members due to retire in June 2021, corporate memory is lost and recruitment fails to provide suitable replacements | 4 x 4 = 16 | Board recruited according to the skills required and following procedures agreed by the Governance paper. | 3 x 3 = 9 | New strategy requires Board to review skill set and ensure it is fit for purpose. | 2023-12-01 | 3 x 3 = 9 | JF/RH | WB | Remove
AE19 | Health and safety. Impact of remote working/ new ways of working on Active Essex team. Need to ensure focus on maintaining health and wellbeing of staff. | 3 x 4 = 12 | Work with host agency to maximise use of technology and inform ECC policy around new ways of working. | 3 x 3 = 9 | Ensure staff are supported around health and wellbeing as ways of working develop through host agency policies and supported by line management structure of ECC. | 2024-12-15 | 2 x 3 = 6 | RH | CR | Remove
AE 21 | Find your active - Behaviour change campaigning | 3 x 4 = 12 | Resources are in place. Provide advise and expertise to add value to delivery, support role out and continue strong advocacy. | 3 x 3 = 9 | Ensure the campaign is successfully delivered and evaluated in order to continue to advocate for additional resources in this space. | 2024-12-15 | 3 x 3 = 9 | HA/GH | CR | Remove
AE8 | Active Essex Board and internal workforce not reflecting the diversity of its community as outlined in Code of Sports Governance | 3 x 4 = 12 | Plans in place including Race Equality Code Plan, Diversity & Inclusion Action Plan & Activity Alliance LEAD plan informing recruitment processes | 3 x 3 = 9 | Execution of action plans across the financial year. Feed into People, Culture Skills work. | ongoing | 3 x 3 = 9 | HC | BM | Remove
AE9 | Active Essex Board and internal workforce not displaying Active Essex values of 'We are Inclusive' and creating an Inclusive Culture | 3 x 4 = 12 | Team & Culture Stretch Group for continuous improvement. Ongoing training for Equality, Diversity & Inclusion including Inclusive Leaders programme | 3 x 3 = 9 | Review recruitment and on-boarding processes for the inclusion of Values expectations. Training log being developed to capture EDI training | ongoing | 2 x 2 = 4 | HC/HW | BM | Remove
AE 13 | Local Delivery Pilot bid is successful with Active Essex continuing to play a lead role in the brokering and facilitation of this project, placing pressure on resources of AP to deliver. | 3 x 3 = 9 | Organisational capacity and operation in line with requirements funding conditions enables project to work effectively | 2 x 3 = 6 | Respond with adapted organisational and programme plan linking AP and LDP outcomes. | 2025-03-15 | 2 x 2 = 4 | JF | WB | Remove
AE 25 | Changes to Ride London Essex cycling event results in the loss of funding and a disconnection with London Marathon Events and Foundation | 3 x 4 = 12 | A funding reduction would result less grant funding being available to LTO's, LMF reached out and a meeting took place inNovember to discuss the future funding partnership. | 3 x 4 = 12 | LMF verbal argeed to provide funding from Sep 2025 to August 2026 and value a potential longer term future funding partnership. Awaitng formally grant paperwork. | 2025-03-01 | 3 x 3 = 9 | RH |  | Remove
AE 20 | Holiday Activities and Food Programme fails to put in place programme structures, project infrastructure and deliverables. | 4 x 4 = 16 | Work with system partners to lever resources, impact on policy and structures required improve outcomes for target audience. | 2 x 2 = 4 | Funding March 2026 to April 2028 confirmed. Continue to advocate the impact of work and keep open communication channels with DoFE for project post Oct 2025 for detail of any changes. | 2025-12-15 | 2 x 2 = 4 | LV | AF
AE 26 | Active Essex Form and Function work is not carried out effectively and efficiently resulting in the loss of staff, a team structure not fit for purpose and a unbalanced budget | 4 x 4 = 16 | Scoping work with ECC done. Staff consultation finished Dec 2024 | 3 x 3 = 9 | Staff selection process taking place. Completed 17th January. New operating model/ structure 6 months into effect. | 2026-03-01 | 2 x 2 = 4 | JF/RH | WB